## Sheet1
MITIGATING JOULE EXPANSION IN MULTI-CELL ATOMIC MEMORY
Proposed Starting Date: Monday 1st of September 2022 | 2022 | 2023 |  |  |  | 2024 |  |  |  | 2025
Budget: £ 369,141.00 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3
Work Package 1: Operation "Kickstart"
Order Optical Components | bar: 2022 Q4
Literature Review: Compile and Write | bar: 2022 Q4 to 2023 Q1
Numerical Simulations of Atomic Ensembles in Optical Tweezers | bar: 2023 Q1 to 2023 Q2
Building the Experimental Optical Set-Up | bar: 2023 Q2 to 2024 Q1
Work Package 2: Experiment and Data
Run Experiments and Analysis of Data | bar: 2024 Q1 to 2024 Q2
Agreement Between Numerical Simulations and Experiment | bar: 2024 Q2 to 2024 Q3
Progress Report | bar: 2024 Q3
Work Package 3: Outreach and Industrial R&D
Participate in R&D of quantum hardware with M2Lasers | bar: 2024 Q4 to 2025 Q3
IEEE International Conference On Quantum Computing and Engineering | bar: 2024 Q4
Organise: Workshop in Advances in Quantum Hardware (WAQC '24): Glasgow, U.K | bar: 2025 Q2
Organise: Workshop in Advances in Quantum Hardware (WAQC '24): Beijing, China | bar: 2025 Q3
Overall Project Valuation | bar: 2025 Q3