## Sheet1
MITIGATING JOULE EXPANSION IN MULTI-CELL ATOMIC MEMORY
Proposed Starting Point: Monday 10th of January 2022
Budget: £ 504000
Work Package (WP) #
| 2022 |  |  | 2023 |  |  | 2024
| Quarter I | Quarter II | Quarter III | Quarter I | Quarter II | Quarter III | Quarter I | Quarter II | Quarter III
Work Package 1: Operation "Kickstart"
Order Optical Components
Literature Review: Compile and Write
Numerical Simulations of Atomic Ensembles in Optical Tweezers
Start Building the Experimental Optical Set-Up
Progress Report
Work Package 2: Experiment and Data
Run Experiments and Analysis of Data
Agreement Between Numerical Simulations and Experiment
Comparison of data with numerical simulations
Progress Report
Work Package 3: Outreach and Industrial R&D
Participate in R&D of quantum hardware with M2Lasers
International Conference in Quantum Electronics and Laser Science
IEEE International Conference On Quantum Computing and Engineering
Organise: Workshop in Advances in Quantum Hardware (WAQC23): Glasgow, U.K
Organise: Workshop in Advances in Quantum Hardware (WAQC23): Beijing, China
Overall Project Valuation