## Sheet1
MITIGATING JOULE EXPANSION IN MULTI-CELL ATOMIC MEMORY
Proposed Starting Point: Monday 1st of September 2022
Budget: £ 384,727.00
Work Package (WP) #
| 2022 | 2023 |  |  |  | 2024
| Quarter IV | Quarter I | Quarter II | Quarter III | Quarter IV | Quarter I | Quarter II | Quarter III | Quarter IV
Work Package 1: Operation "Kickstart"
Order Optical Components
Literature Review: Compile and Write
Numerical Simulations of Atomic Ensembles in Optical Tweezers
Start Building the Experimental Optical Set-Up
Work Package 2: Experiment and Data
Run Experiments and Analysis of Data
Agreement Between Numerical Simulations and Experiment
Progress Report
Work Package 3: Outreach and Industrial R&D
Participate in R&D of quantum hardware with M2Lasers
IEEE International Conference On Quantum Computing and Engineering
Organise: Workshop in Advances in Quantum Hardware (WAQC '24): Glasgow, U.K
Organise: Workshop in Advances in Quantum Hardware (WAQC '24): Beijing, China
Overall Project Valuation